## Team
Initials | First | Last | Email | GitHub Username
vg | Vignesh | Mohan | vigmohan95@gmail.com | Vigzm1995
ab | Anirudh | Bezzam | abezzam@stevens.edu | Abezzam10
th | Tanvi | Hanamshet | tanvihanamshet412@gmail.com | Tanvi-412
lx | Lifu | Xiao | leaf_hsiao@outlook.com | leaf-hsiao
yz | Yuan | Zhang | byrd.zhang@gmail.com | Kybeth
|  |  | GitHub Repository: | https://github.com/Kybeth/SSW555-GEDCOM-Develop-Team02

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | Vignesh Mohan | Done
1 | US02 | Birth before marriage | Vignesh Mohan | Done
1 | US03 | Birth before death | Anirudh Bezzam | Done
1 | US04 | Marriage before divorce | Anirudh Bezzam | Done
1 | US05 | Marriage before death | Tanvi Hanamshet | Done
1 | US06 | Divorce before death | Tanvi Hanamshet | Done
1 | US07 | Less then 150 years old | Lifu Xiao | Done
1 | US08 | Birth before marriage of parents | Lifu Xiao | Done
1 | US09 | Birth before death of parents | Yuan Zhang | Done
1 | US10 | Marriage after 14 | Yuan Zhang | Done
2 | US11 | No bigamy | Vignesh Mohan | Assigned
2 | US12 | Parents not too old | Vignesh Mohan | Assigned
2 | US13 | Siblings spacing | Anirudh Bezzam | Assigned
2 | US14 | Multiple births <= 5 | Anirudh Bezzam | Assigned
2 | US15 | Fewer than 15 siblings | Tanvi Hanamshet | Assigned
2 | US16 | Male last names | Tanvi Hanamshet | Assigned
2 | US17 | No marriages to children | Lifu Xiao | Assigned
2 | US18 | Siblings should not marry | Lifu Xiao | Assigned
2 | US19 | First cousins should not marry | Yuan Zhang | Assigned
2 | US20 | Aunts and uncles | Yuan Zhang | Assigned
3 | US21 | Correct gender for role | Vignesh Mohan | Assigned
3 | US22 | Unique IDs | Vignesh Mohan | Assigned
3 | US23 | Unique name and birth date | Anirudh Bezzam | Assigned
3 | US24 | Unique families by spouses | Anirudh Bezzam | Assigned
3 | US25 | Unique first names in families | Tanvi Hanamshet | Assigned
3 | US26 | Corresponding entries | Tanvi Hanamshet | Assigned
3 | US27 | Include individual ages | Lifu Xiao | Assigned
3 | US28 | Order siblings by age | Lifu Xiao | Assigned
3 | US29 | List deceased | Yuan Zhang | Assigned
3 | US30 | List living married | Yuan Zhang | Assigned
4 | US31 | List living single | Vignesh Mohan | Assigned
4 | US32 | List multiple births | Vignesh Mohan | Assigned
4 | US33 | List orphans | Anirudh Bezzam | Assigned
4 | US34 | List large age differences | Anirudh Bezzam | Assigned
4 | US35 | List recent births | Tanvi Hanamshet | Assigned
4 | US36 | List recent deaths | Tanvi Hanamshet | Assigned
4 | US37 | List recent survivors | Lifu Xiao | Assigned
4 | US38 | List upcoming birthdays | Lifu Xiao | Assigned
4 | US39 | List upcoming anniversaries | Yuan Zhang | Assigned
4 | US40 | Include input line numbers | Yuan Zhang | Assigned

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2019-09-17 | 40 |  | 0
2019-10-01 | 30 | 10 | 100 | 315 | 19.0476
2019-10-15 | 20 | 10 | 627 | 1090 | 29.0092
2019-10-29 | 10 | 10 | 575 | 310 | -10.0645

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US01 | Dates before current date | Vignesh Mohan | Coding | 50 | 60 | 8 | 30
US02 | Birth before marriage | Vignesh Mohan | Coding | 50 | 60 | 10 | 30
US03 | Birth before death | Anirudh Bezzam | Coding | 40 | 50 | 15 | 35
US04 | Marriage before divorce | Anirudh Bezzam | Coding | 40 | 60 | 15 | 30
US05 | Marriage before death | Tanvi Hanamshet | Coding | 50 | 70 | 20 | 30 | 2019-09-01
US06 | Divorce before death | Tanvi Hanamshet | Coding | 50 | 70 | 20 | 30 | 2019-09-01
US07 | Less then 150 years old | Lifu Xiao | Done | 50 | 60 | 12 | 45(pair) | 2019-09-28
US08 | Birth before marriage of parents | Lifu Xiao | Done | 40 | 60 | 14 | 100 | 2019-09-30
US09 | Birth before death of parents | Yuan Zhang | Done | 40 | 60 | 14 | 20(pair) | 2019-09-28
US10 | Marriage after 14 | Yuan Zhang | Done | 30 | 60 | 12 | 30 | 2019-10-01
Review Results
Keep doing:
Communicate often and encourage each other
Take responsibility bravely when not doing well
Avoid:
Do things late before the ddl

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US11 | No bigamy | Vignesh Mohan | Assigned | 15 | 45 | 23 | 360 | 2019-10-15
US12 | Parents not too old | Vignesh Mohan | Assigned | 15 | 45 | 23 | 360 | 2019-10-15
US13 | Siblings spacing | Anirudh Bezzam | Assigned | 15 | 40 | 20 | 30 | 2019-10-15
US14 | Multiple births <= 5 | Anirudh Bezzam | Assigned | 15 | 40 | 15 | 30 | 2019-10-15
US15 | Fewer than 15 siblings | Tanvi Hanamshet | Assigned | 15 | 40 | 12 | 30 | 2019-10-15
US16 | Male last names | Tanvi Hanamshet | Assigned | 15 | 40 | 11 | 30 | 2019-10-15
US17 | No marriages to children | Lifu Xiao | Assigned | 13 | 30 | 11 | 90 | 2019-10-15
US18 | Siblings should not marry | Lifu Xiao | Assigned | 13 | 30 | 13 | 60 | 2019-10-15
US19 | First cousins should not marry | Yuan Zhang | Assigned | 15 | 30 | 19 | 80 | 2019-10-15
US20 | Aunts and uncles | Yuan Zhang | Assigned | 15 | 30 | 20 | 20 | 2019-10-15
1090
Review Results
Start early | Refactor to use class structure and build automated test
Keep doing:
Communicate often and encourage each other
Take responsibility bravely when not doing well
Avoid:
Do things late before the ddl
Mess with the github

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US21 | Correct gender for role | Vignesh Mohan | Assigned | 15 | 120 | 12 | 60 | 2019-10-29 | main.py | US21 | 157-169 | test.py | test_US21 | 127-130
US22 | Unique IDs | Vignesh Mohan | Assigned | 20 | 60 | 18 | 120 | 2019-10-29 | main.py | US22 | 172-194 | test.py | test_US22 | 132-135
US23 | Unique name and birth date | Anirudh Bezzam | Assigned | 20 | 60 | 7 | 15 | 2019-10-28 | main.py | US23 | 270-279 | test.py | test_US23 | 65-73
US24 | Unique families by spouses | Anirudh Bezzam | Assigned | 20 | 70 | 17 | 15 | 2019-10-28 | main.py | US24 | 281-295 | test.py | test_US24 | 55-63
US25 | Unique first names in families | Tanvi Hanamshet | Assigned | 20 | 60 | 10 | 15 | 2019-10-29 | main.py | US25 | 299-312 | test.py | test_US25 | 165-169
US35 | List recent births | Tanvi Hanamshet | Assigned | 20 | 80 | 20 | 20 | 2019-10-29 | main.py | US26 | 317-332 | test.py | test_US26 | 171-174
US27 | Include individual ages | Lifu Xiao | Assigned | 20 | 60 | 11 | 15 | 2019-10-28 | main.py | US27 | 390-400 | test.py | test_US27 | 151-154
US28 | Order siblings by age | Lifu Xiao | Assigned | 20 | 60 | 14 | 20 | 2019-10-28 | main.py | US28 | 402-415 | test.py | test_US28 | 156-161
US29 | List deceased | Yuan Zhang | Assigned | 18 | 60 | 8 | 15 | 2019-10-28 | main.py | US29 | 501-509 | test.py | test_US29 | 113-118
US30 | List living married | Yuan Zhang | Assigned | 18 | 60 | 9 | 15 | 2019-10-28 | main.py | US30 | 511-519 | test.py | test_US30 | 120-125
310
Review Results
Keep doing:
Write each one's code in different area to avoid conflicting
Spliting tasks in a sprint into smaller phases, and assign ddl to each phase
Avoid:
Writing tons of code without enough comments. This really makes it hard for team members to understand your code

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US31 | List living single | Vignesh Mohan | Assigned | 20 | 60
US32 | List multiple births | Vignesh Mohan | Assigned | 20 | 60
US33 | List orphans | Anirudh Bezzam | Assigned | 19 | 20
US34 | List large age differences | Anirudh Bezzam | Assigned | 25 | 20
US41 | Include partial dates | Tanvi Hanamshet | Assigned | 19 | 20
US36 | List recent deaths | Tanvi Hanamshet | Assigned | 25 | 20
US37 | List recent survivors | Lifu Xiao | Assigned | 20 | 30
US38 | List upcoming birthdays | Lifu Xiao | Assigned | 20 | 30
US39 | List upcoming anniversaries | Yuan Zhang | Assigned | 20 | 30
US40 | Include input line numbers | Yuan Zhang | Assigned | 20 | 30

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to children | Parents should not marry any of their children
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)